## FMEA Template
FAILURE MODES & EFFECTS ANALYSIS WORKSHEET
Process / Product: | Painting Dinning Room |  |  | FMEA Date (Original):
WHEN Item/ Process Step | WHAT Potential Failure Mode | Potential Effect(s) of Failure | Severity | WHY Potential Cause(s) of Failure | Occurrence | Current Controls | Detection | RPN | Recommended Actions (Response Plans - Containment, SOP's, Control Plans) | Responsibility and Target Date Completion | Action Taken | Severity | Occurrence | Detection | RPN
3 - Prepare Room | Don't cover floor | Damage to flooring | 7 | Incorrect drop cloth size | 7 | Measure room | 6 | 294 | Measure room twice, write it down | Barb 3/26/2012 | Measured twice and wrote done specs. | 7 | 7 | 3 | 147
4 - Paint | Use wrong color | Have to repaint | 8 | Bad lighting | 8 | Paint small section using sample jar of paint | 4 | 256 | Use full sample jar when painting area of wall | Barb 3/26/2012 | pending | 8 | 6 | 3 | 144
5 - Clean-Up | Damage funiture - returning it | Funiture repair / repurchase | 6 | Move funiture by one person | 6 | wife is in room at same time and monitors | 4 | 144 | None - accept risk |  |  | 6 | 6 | 4 | 144
4 - Paint | Foreign object damage (contaminate paint) | Return for more supplies | 4 | Eating food in room while painting | 7 | Prohibit eating food in room | 5 | 140 | None - accept risk |  |  | 4 | 7 | 5 | 140
5 - Clean-Up | Spill paint | Damage to flooring | 7 | Tripped on can | 9 | None | 7 | 441 | Put can in corner | Mark 10/26/2011 | pending | 7 | 6 | 3 | 126
4 - Paint | Spill paint | Added work / damage to flooring / added cost | 6 | Tripped on can | 9 | None | 6 | 324 | Put can in corner | Mark 3/26/2012 | pending | 6 | 7 | 3 | 126
5 - Clean-Up | Spill paint | Added work/ added cost | 6 | Tripped on can | 9 | None | 6 | 324 | Put can in corner | Mark 10/26/2011 | pending | 6 | 7 | 3 | 126
5 - Clean-Up | Damage fresh paint | Have to repaint | 7 | Remove tape too late | 7 | None formalized | 8 | 392 | Set timer after painting to remove tape | Barb 10/26/2011 | pending | 7 | 6 | 3 | 126
5 - Clean-Up | Damage fresh paint | Have to repaint | 7 | Move funiture by one person | 6 | None | 7 | 294 | wife is in room at same time and monitors | Barb 10/26/2011 | All furniture moved with Barb helping | 7 | 6 | 3 | 126
1 - Select Supplies | Miscalculate required paint | Run out of paint - have to buy more | 5 | Measured incorrectly | 8 | None | 8 | 320 | Double check measurement, add 10% | Barb 3/26/2012 | Did double check and added 10% as defined | 5 | 6 | 4 | 120
2 - Obtain Supplies | Store is out of material (supply) | Delay / added cost | 4 | Poor store inventory | 7 | Have back-up store planned | 4 | 112 | None - accept risk |  |  | 4 | 7 | 4 | 112
3 - Prepare Room | Tape not installed properly | Have to repaint | 7 | Bad lighting | 8 | Use Halogen lights | 2 | 112 | None - accept risk |  |  | 7 | 8 | 2 | 112
4 - Paint | Don't paint even / thin spots | Have to repaint | 7 | Bad lighting | 8 | Use Halogen lights | 2 | 112 | None - accept risk |  |  | 7 | 8 | 2 | 112
1 - Select Supplies | Used the incorrect brush | the paint runs or clumps | 6 | Picked out wrong brush at store | 6 | Double check brush against supply checklist | 7 | 252 | When painting sample use the same brush as planned for job | Mark 3/26/2012 | pending | 6 | 6 | 3 | 108
3 - Prepare Room | Damage funiture - moving it | Funiture repair / repurchase | 6 | Move funiture by one person | 6 | None | 6 | 216 | wife is in room at same time and monitors | Barb 3/26/2012 | pending | 6 | 6 | 3 | 108
1 - Select Supplies | Pick the wrong paint - type (flat, semi-gloss) | Re-do project | 8 | Incomplete planning | 6 | Paint small section using sample jar of paint | 4 | 192 | Use full sample jar when painting area of wall | Barb 3/26/2012 | pending | 8 | 6 | 2 | 96
1 - Select Supplies | Pick the wrong paint - color | Re-do project | 8 | Improper blending at hardware | 5 | Paint small section using sample jar of paint | 4 | 160 | Use full sample jar when painting area of wall | Barb 3/26/2012 | pending | 8 | 6 | 2 | 96
5 - Clean-Up | Discover paint doesn’t match | Have to repaint | 8 | Paint not mixed properly | 4 | None | 5 | 160 | Stir all cans and blend cans | Mark 10/26/2011 | pending | 8 | 4 | 3 | 96
4 - Paint | Fall off of ladder | Delay due to injury | 9 | Not wearing shoes | 5 | None | 8 | 360 | Check list with "wearing shoes" | Barb 3/26/2012 | check list created and ready to use | 9 | 5 | 2 | 90
1 - Select Supplies | Used the incorrect brush | the paint runs or clumps | 6 | Bad advice | 6 | None | 7 | 252 | When painting sample use the same brush as planned for job | Mark 3/26/2012 | pending | 6 | 5 | 3 | 90
4 - Paint | Ruin Clothes | Added cost to replace | 5 | Wore good clothes instead of painting clothes. | 8 | None | 5 | 200 | Put proper clothing on the checklist | Barb 3/26/2012 | Project checklist created | 5 | 8 | 2 | 80
2 - Obtain Supplies | Store is out of material (discontinued) | Color mis-match between paint and curtains | 8 | Delay in ordering paint once selected | 5 | None | 4 | 160 | Buy paint as soon as the color is chosen | Mark 3/26/2012 | alternate paint store confirmed | 8 | 5 | 2 | 80
4 - Paint | Paint tracked throught house | Added cost / clean up | 5 | Improper control of children | 6 | None | 8 | 240 | Paint when children are not home | Barb 3/26/2012 | pending | 5 | 6 | 2 | 60
2 - Obtain Supplies | Don't buy following checklist | Second trip for more supplies | 5 | Forgot checklist and relied on memory | 8 | None | 5 | 200 | Mark doesn't leave house without checklist | Barb 3/26/2012 | check list followed up | 5 | 6 | 2 | 60
3 - Prepare Room | Run out of Tape | Return for more supplies | 4 | Underestimate required tape | 7 | None | 6 | 168 | Purchase extra roll of tape | Mark 3/26/2012 | Extra roll purchased | 4 | 7 | 2 | 56
1 - Select Supplies | Choose wrong size drop cloth - too big | Have to fold drop cloth | 2 | Measured incorrectly | 4 | Measure room twice | 7 | 56 | None - accept risk |  |  | 2 | 4 | 7 | 56
4 - Paint | Paint tracked throught house | Added cost / clean up | 5 | Improper control of pets | 6 | Invisible Fence in kitchen | 5 | 150 | Put dog in crate when painting | Barb 3/26/2012 | pending | 5 | 5 | 2 | 50
3 - Prepare Room | Tape not installed properly | Remove and re-apply tape | 3 | Bad lighting | 8 | Use Halogen lights | 2 | 48 | None - accept risk |  |  | 3 | 8 | 2 | 48
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0 | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0 | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0

## Operational Definitions
Severity Ratings
Effect | Rank | Criteria
Very High | 9 - 10 | Failure affects safety or involves noncompliance to government regulations. May endanger machine or assembly operator (9 with warning, 10 without warning)
High | 7 - 8 | High degree of customer dissatisfaction due to the nature of the failure, such as inoperable item or system. Failure does not involve safety or government regulation. May result in serious disruption to subsequent processing or assembly operations and/or require major rework.
Moderate | 4 - 5 - 6 | Failure causes some customer dissatisfaction which may include discomfort or annoyance. Customer will notice item or system performance deterioration. This may result in unscheduled rework/repair and/or damage to equipment.
Low | 2 -3 | Due to the nature of this failure, the customer experiences only slight annoyance. Customer will probably notice slight deterioration of the item or system performance or a slight inconvenience with a subsequent process or assembly operation, i.e. minor rework.
Minor | 1 | Unreasonable to expect that the minor nature of this failure will have any noticable effect on item or system performance or subsequent process or assembly operation. Customer will most likely not be able to detect the failure.
Occurrence Ratings
Occurrence Ratings | Rank | Criteria | Failure Rates
Very High | 10 | Failure is almost inevitable | >1 in 3
| 9 |  | 1 in 6
High | 8 | This process or similar processes have often failed | 1 in 15
| 7 |  | 1 in 50
Moderate | 6 | This process or similar processes have experienced occasional failures, but not in major proportions | 1 in 150
| 5 |  | 1 in 800
| 4 |  | 1 in 4,500
Low | 3 | Isolated failures associated with similar processes | 1 in 30,000
Very Low | 2 | Only isolated failures associated with this process or almost identical processes | 1 in 150,000
Remote | 1 | Failure unlikely. No failures ever assocaited with this process or almost identical processes | <1 in 1,500,000
Detection Ratings
Detection | Rank | Criteria
Absolute certainty of non-detection | 10 | Controls will not or can not detect the existence of a failure. No known controls available to detect failure mode.
Very low | 9 | Controls probably will not detect the existence of failure mode
Low | 7-8 | Controls have a poor chance of detecting the existence of failure mode
Moderate | 5-6 | Controls may detect the existence of a failure mode.
High | 3 - 4 | Controls have a good chance of detecting failure mode, process automatically detects failure mode.
Very High | 1 - 2 | Current controls almost certain to detect the failure mode. Reliable detection controls are known with similar processes. Process automatically prevents further processing.